Green Partners project work planning tool – EXAMPLE*

- Hennepin County environmental education website: www.hennepin.us/environmentaleducation

- Hennepin County environmental education literature order form: https://environmentalresources.hennepin.us/items

| Waste reduction project - EXAMPLE |  |  |  |  |
| --- | --- | --- | --- | --- |
| Date | Activity | Tasks | Resources & Tools | Notes |
| September | Decorate reusable bags, discuss and share stories | - Order reusable bags - Materials to decorate bags - Order window clings | - Environmental education activity guide - Remember the Bags window clings - Green Partners barriers discussion guide | Take notes |
| October | Children’s recycling activities | - Reserve learning kit - Order literature - Gather recycling books and games | - Hennepin County literature: Recycling Guide - Hennepin County youth recycling learning kit - Hennepin County recycling activity book |  |
| November | Barriers and benefits discussion | - Facilitate discussion of barriers to toxicity reduction with parents | - Green Partners barriers discussion guide | Submit barriers report, due Nov. 30 |
| December | Schedule field trip to a waste facility | - Schedule field trip for February - Arrange for bus - Send invitations | - BPTS tour registration site - HERC tour registration site |  |
| January | Practice using shopping bag | - Handout window clings - Ask parents to report out - Share parent quotes in newsletter | - Hennepin County Remember the Bags window clings | Get permission to use quotes |
| February | Field trip to Hennepin County Drop-off Facility | - Send reminder to participants - Pick up snacks for bus trip - Take photos during trip | - Hennepin County literature: Drop-off Facility & How to identify household hazardous waste brochures | Get permission to use photos |
| March | Make non-toxic cleaners | - Order spray bottles and supplies - Prepare cleaner making stations | - Hennepin County non-toxic spray bottles, vinegar, dish soap, measuring spoons, funnels | Buy reused materials $1.15 per bottle |
| April | On-site waste sort | - Prepare waste sort stations - Request waste sort trunk - Take photos - Report out results | - Waste sort trunk (aprons, gloves, sorting tools, goggles, etc.) | Get permission to use photos |
| May | Waste prevention shopping trip | - Prepare workshop - Request county staff to review workshop materials | - Hennepin County packaging waste learning kit |  |
| June | Waste prevention video | - Create video plan and get props - Film and edit video |  |  |
| July | Event tabling | - Recruit volunteers - Prepare wheel of waste reduction |  |  |
| August | Submit final report | - Tally receipts and purchases - Tally project outcomes - Write report - Submit report | - Final report document - Budget report document - Outcomes report guide www.hennepin.us/greenpartners | Call or email with questions |

Green Partners project work planning tool

- Hennepin County environmental education website: www.hennepin.us/environmentaleducation

- Hennepin County environmental education literature order form: https://environmentalresources.hennepin.us/items

| PROJECT TITLE: |  |  |  |  |
| --- | --- | --- | --- | --- |
| Date | Activity | Tasks | Resources & Tools | Notes |
| September |  |  |  | Orientation, Sep. 11, 2019 |
| October |  |  |  |  |
| November |  |  |  | Barriers to action discussion, report due Nov. 30, 2019 |
| December |  |  |  |  |
| January |  |  |  |  |
| February |  |  |  |  |
| March |  |  |  |  |
| April |  |  |  |  |
| May |  |  |  |  |
| June |  |  |  |  |
| July |  |  |  |  |
| August |  |  |  | Final report due, Aug. 31, 2020 |